## On Time Delivery
To View this Dashboard in the Manner it should appear for presentation charts and published reports, Please view this page in Print Preview Mode.
Top 5 Action Items to Address Drivers
Driver | Action Description | Status | Status Description | Owner | Original Due Date | Current Due Date
Late Supplier Deliveries | Monthly reporting to suppliers on delivery & quality metrics. | On track | Report Cards Implemented. | Adam | 2007-05-21 | 2007-05-21
Late Supplier Deliveries | Arrange face to face meetings with top offenders. | On track | Meetings Complete with top 10 Suppliers. | Beth | 2007-06-15 | 2007-06-15
Late Supplier Deliveries | Review and approve supplier's corrective action plan. | Caution | Corrective Action Plan in Place for 2 major Suppliers | Carlos | 2007-07-15 | 2007-09-15
xyz Cell Always Late | Kaizen Event to focus on improving throughput by 40% and improve labor efficiency by 35% | On track | Event held 5/1. 25% throughput improvement in May. Labor Efficiency Increase of 30% | Doreen | 2007-05-21 | 2007-05-21
Unrealistic Promise Date | Focus on custom products to provide realistic ATP based on inventory and leadtime of components. | Problem | Continued lack of progress. Re-structured and focused team. Developing detailed plan. | Earnest | 2007-06-15 | 2007-08-15

## Data
ON TIME DELIVERY TREND
Month | 2001-01-01 | 2001-02-01 | 2001-03-01 | 2001-04-01 | 2001-05-01 | 2001-06-01 | 2001-07-01 | 2001-08-01 | 2001-09-01 | 2001-10-01 | 2001-11-01 | 2001-12-01
Target | 72% | 75% | 78% | 81% | 84% | 86% | 88% | 90% | 91% | 92% | 93% | 94%
Actual | 2001-01-01: 70%; 2001-02-01: 74%; 2001-03-01: 74%; 2001-04-01: 81%; 2001-05-01: 86%; 2001-06-01: 85%
Definition
The percentage of sales order line items that ship complete on or before the original customer promise date, for all line items shipped in the month.
Pareto Analysis of Drivers
Reason | 2001-01-01: % effect
Late Supplier Deliveries | 2001-01-01: 40%
xyz Cell Always Late | 2001-01-01: 20%
Unrealistic Promise Date | 2001-01-01: 15%
Orders on Credit Hold | 2001-01-01: 10%
Low Yield on part abc | 2001-01-01: 10%
Engineering Change Orders | bar: 2001-01-01
Remaining % Unassigned | bar: 2001-01-01

## Goal Gage
This Performance Gage was Created On-line FREE with iDash Executive Dashboard then cut and pasted into the main Dashboard.
Click here to register for a free iDash Dial Indicator Generator
VERY EASY TO USE!
A couple of other pretty good sources for Excel Dashboard Generators:
Click here for the Excel Dashboard Kit - Free Trial
Click here for the FREE JaxWorks Excel Financial Dashboard (VERY complex and VERY pretty… your CFO will love it!) -- scroll halfway or so down the page, alphabetically, to "Financial Dashboard".